## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG
Project Name: |  |  | You might also like
National Center: |  |  | <required>
Project Manager Name: |  |  | <required>
Project Description: |  |  | <required>
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | High | Medium | Red | Team might not have skill set to complete all project work. All team members are fairly new to (Java Servlets/JSF). When the project team needs to obtain new skills for the project, there's a risk that the learning curve will slow all productivity. Team members have negative attitudes towards the project and each other, and result in low team motivation. | If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Schedule approaches the required start date with no identification of required skill sets. | Contingency | Erin’s colleagues have an expertise and will be able to offer help – hopefully ensuring the team is never completely stuck. Considering as this project is a learning exercise for university study, all team members are expected to learn new skills. This is not a problem but an expectation, as long as research is done in a timely manner. All team members will eventually feel a lack of motivation. Honest communication can clear up disputes. | Ask stakeholder to step in and help solve issues and explain their solutions.
2 | Open | Medium | Medium | Yellow | Stakeholder become disengaged and fails to support the project. Stakeholders neglect communication and meetings, and the project struggles as a result. There may be disagreement between stakeholders that can interrupt project progress. | Project becomes unorganised and conflicted, project schedule will fall behind. | Organizational/Change Management Schedule | Stakeholders take longer that 24hrs to respond. Stakeholders disagree. Stakeholders are not using push communication (slack.com) | Mitigation | Have a variety of stake holders become a part of the project development. Input from all stakeholders will be valued but the end decision falls to the team. The project will not be tailored to one specific stakeholder. | Remove stakeholders from project.
3 | Open | Medium | Medium | Yellow | work, family, study and other commitments can affect how much time each team member can contribute. All team members have other priorities that must also be met in their daily activities. | Deadlines are not met or work quality suffers | Schedule | Team member not putting in enough hours each week to meet deadlines | Mitigation | Some team members are working, so could be a potential issue. Need to make sure time off can be taken if it becomes necessary. Share the workload evenly | Put a strike against an inactive team member. Remove a team member with 3 strikes.
4 | Open | High | Medium | Red | Scope of the project is poorly defined and can be open for interpretation. Necessary activities are completely missing from the scope. | The project will not be complete or functional | Project Management Feasibility | Activities that are in the requirements are outside of the project scope. | Mitigation | Scope must be clear and concise. The Scope will be reviewed by all team members and stakeholders to look for future problems and discuss solutions. | Stakeholders will assist a rewrite or reclarification of work items to make the scope clearer.
5 | Open | Medium | Low | Green | Trouble obtaining sufficient data for the project to work effectively from the Nintendo, Steam, XBox, and Playstation servers. Game data will be obtained from e-shop servers using APIs where available and web crawlers where not. Games data scraper fails (i.e. API changes, or the structure of a scraped page changes, etc) | Without the data from the Nintendo servers, the project will not function. The website is dependant on continues access to these servers. | Data/Information Technology | The website will be unable to access the game title, product code, icon, etc. | Avoidance | Design for quick alteration/expandability of data scraper. Erin and the stakeholders have experience with retrieving the relevant data from the Nintendo servers and can assist the case of a fault | Use the PlayStation, Steam and Xbox servers instead or as well
6 | Open | Medium | Medium | Yellow | Team members add their own features that aren't in the requirements or change requests. | Project goes outside the scope. Conflicts can arise with systems that where not originally designed to be integrated into project. | Project Management | Project has errors because a team member is trying to integrate a feature the system is not designed to integrate. E.g. a forum or following feature | Acceptance | If the team wants to add a new feature, add it to the change requests before implementation. | If the team does not like suggested feature or it is unfeasible, remove / disregard feature.
7 | Open | Medium | Medium | Yellow | Too many change requests at once make project complex and confusing. No priorities or order to change log. Change requests conflict with the project requirements. | Change requests conflict with each other and cause confusion among the team | Project Management | Change log becomes backlogged with changes that need to be sorted. | Mitigation | All changes should be discussed as a group. Work on only a couple of changes at a time. Sort the non-essential changes lower on a prioritised list of changes. | Remove change log and find alternative methods.
8 | Open | Medium | Medium | Yellow | Lack of team communication leads to misinterpretation and confusion. The stakeholders and instructor and not kept informed. Lack of communication will slow any necessary support. | Team members may not have the skills required to preform their task and are unable to get sufficient help. Project schedule may be hindered and team communication may dissolve. | Project Resources Budget Schedule | Team members are not using push communication and updating their work to repository consistently. | Mitigation | Communicate needs to be constant and clear. Ideas may need to be discusses many times in different ways before the whole team understands a new concept. Stakeholders and instructor have been added to slack.com, our selected push communication mechanism. | If lack of communication is causing work to be handed in late, put a strike against an inactive team member. Remove a team member with 3 strikes.
9 | Open | High | Medium | Red | Architecture is not flexible or capable of supporting change requests and must be revised. Design fails to meet purpose requirements. The design is inefficient and full of errors. | Project will not function and the foundations of the project must be revised. The website will not pass the requirements set out at the start of the project. | Reliability of Systems Data and information | The system in not capable of supporting new changes. E.g. a forum cannot be added because the foundations do not support that integration. | Mitigation | The design needs to be both discussed with the whole team, stakeholders and instructors to catch any floors early in the design process. Design must be flexible and built for future expansion in mind. | If the architecture is found to be inflexible late into development the team will be forced to keep the project simple as it is too late to fix the foundations of the project architecture.
10 | Open | High | Low | Yellow | Requirements fail to align with system. Requirements are unfinished and have noticeable holes. Requirements are unclear, confusing and open to interpretation. | Project requirements need to be updated, as such project schedule may be hindered. | Overall Project Failure Schedule Project resources Reliability of systems | E.g. the website is required to be viewed at a reduced viewport size and touch interface as it will be accessed on a mobile devises. There must be a set of requirements for desktop and mobile integration. | Mitigation | An accurate use case model that clearly demonstrates the system requirements. Display of key domain concepts and the data required to support the system. Clear analysis of non-functional requirements. | Stakeholders will assist a rewrite or reclarification of work items to make the requirements align with the system
11 | Open | Low | Medium | Green | Slow decisions will delay the project. There are no decision turnaround time guidelines. Decisions are incomplete, don’t resolve the issues or create more issues. | Project becomes unorganised and conflicted, project schedule will fall behind. | Strategic Schedule | Decisions are falling behind workload and project grinds to a halt while problems are slowly discussed. | Mitigation | Establish guidelines for decision turnaround time. Decisions that directly affect the project must be discussed between the whole team. | Elect a leader, and they can make quick executive decisions.
12 | Open | High | Low | Yellow | Team fails to follow methodology set out in charter. Team becomes hard to manage. | Project becomes unorganised and conflicted, project schedule may be hindered. | Overall Project Failure Schedule | Team member not putting in enough hours each week to meet deadlines or refuse to finish aloted work | Mitigation | Each team member has a role and responsibility that is rotated and updated weekly depending on what tasks and activities the group decides need completing. There is a three-strike policy set in place minimise laziness. | Put a strike against an inactive team member. Remove a team member with 3 strikes.
13 | Open | Low | Low | Green | There is an Insufficient sample size of people to both review games and test for errors in the project | Not all games will be rated as there are no current user who had played that game. There may be errors that go unnoticed throughout the development period | Project Resources | Games of no ratings. Errors start showing up after the project has been finalised. | Contingency | Main dedicated stakeholder is soon moving to NZ so won’t be available for a time. However, the project is interesting enough to attract testers simply by putting out a message to social media. | A webserver is available so it will be instantly accessible to anyone who wants to test it (after deployment)
| Open | Medium | Medium | Yellow | A member changes project environment without consultation | A lot of extra work to troubleshoot without any benefit being added to the project. | Strategic Schedule | Development slows down | Mitigation | Affected member puts in extra time. | Affected member buys a new computer.
| Open | Low | Low | Green | Game data servers APIs are restricted | Scraping may fail after a period of time | Project resources | Games not appearing and the database being a lot smaller than expected | Contingency | Applying for multiple free API accounts. | Buying for a paid API account
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on K6: • Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on L6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources