## Initial
|  | Github Issue | Action | Erin | Hugh | Shailesh | Somer
Search For Game
Issue | Games missing | - | No present action due to additional costs | There are too many sorts of problems that cause the games to not get picked up by the scraper, it would be infeasible to get every single game in existence to work, the current list of games is sufficient for demonstration purposes | For the completion of this assignment, the current database has a large enough pool of games to show the funtionality of the site. A larger database is simply not feasible, or required for this sort of project. |  | Mostly just due to the database not being complete. Could be resolved by avoiding steam's rate limiting by making requests from more than 1 IP address, maybe multiple VMs? Similar to the SSL certificate - probably not worth investing too much time/money looking into during this project
Sign Up
Issue | Confirmation email not sent | - | No action? | We don't send confirmation emails, but this is something that could be looked at post-assessment if we wanted to continue the project | We don't send confirmation emails |  | We don't send confirmation emails
Issue | Invalid username and email | - | Nonrepeatable and not repeated in followup No action | Must be user error | have not been able to replicate |  | The system should have mentioned the reason (e.g. too short a password or username) - I can't repeat this issue
Suggestion | Use SSL | - | No action | This would cost money, so not needed for just a uni project | This would be a nice to have, but for this assignment it is not feasible or required. |  | Very valid point but for the scope of this project - seems overkill especially to buy an SSL certificate with less than a month left in the subject
Issue | Site runs slowly on mobile platforms | - | Nonrepeatable No action | Works fine for me - must be the user's mobile device. Something to investigate if the project was continued post-assessment | have not been able to replicate |  | Seems to run the same on my mobile as on PC - I can't repeat this issue
Rate Game
Suggestion | Initially didn't see the stars to rate a game | #14 | Resized the stars |  |  |  | A potentially easy fix - maybe just resizing the stars?
Set Game Preferences
View a Recommendation
Sign Out
Suggestion | Re-order the user options menu and put sign out last | #13 | Re-ordered the list |  | completed |  | Done
Final Impressions
Suggestion | Design feels like a basic wordpress website. A nice own design would make the website more appealing | - | No action |  | This is more an opinion than a problem. I actually really like the look of the website, but do agree that it basic and would be ironed out if we had more time. |  | Fair point - possibly something to look into if the project gets developed further one day, but for the time being I suggest we stick with our design
Issue | Re-signing in is telling me that I have an incorrect username and password even though I am using the correct one | - | No action? | Unable to replicate the issue | This could be user error, I was unable to replicate. |  | Not a lot of info offered, and validation should be the same for sign in as sign up (I checked) so very likely the details entered just didn't match

## Followup
|  | Github Issue | Action | Erin | Hugh | Shailesh | Somer
Search For Game
Issue | Games missing | - | No present action due to additional costs | A big job that can be investigated post-assessment if the project is continued |  |  | Mostly just due to the database not being complete. Could be resolved by avoiding steam's rate limiting by making requests from more than 1 IP address, maybe multiple VMs? Similar to the SSL certificate - probably not worth investing too much time/money looking into during this project
Sign Up
Rate Game
Suggestion | "Sign in to rate" button on specific games page doesn't work | #17 | Made button function the same as "login" button |  |  |  | Fair - easy fix, just making button act same as login button
Set Game Preferences
Suggestion | Odd characteristics - everybody would pick "fun" | #18 | Removed fun characteristic and added suggested characteristics |  |  |  | Very valid suggestion
View a Recommendation
Suggestion | More than one recommendation per person | - | No action | Already multiple recommendations - have to click next recommendation |  |  | User might have missed the "View next recommendation" button
Issue | Duplicate genres | #19 | No present action | Can hide extra genres as they are spotted |  |  | Very valid issue - is caused by multiple stores having slightly varied genre names - would need to add genre remapping in order to resolve. Simply deleting the duplicates won't work, as the games using the duplicate genres will simply cease to have that genre Possibly unable to do in the timeframe
Suggestion | Too many generic genres from steam e.g. "Includes source SDK" | - | Hidden some of the more generic genres |  |  |  | Fair point, perhaps hide some of the more generic genres. Might be a good idea to eventually move some of the genres such as that to characteristics and give allow characteristics to be boolean rather than star based
Sign Out
Suggestion | Have a button rather than "Sign out" being part of the dropdown | - | No action | This could be done if we run out of things to do at the end (unlikely) as it is a reasonable suggestion |  |  | Having it in the dropdown only is fairly common practice (e.g. google, github, steam)
Final Impressions
Issue / Suggestion | Clicking "Crysis 2 Max edition" in the browse hid the "show recommendation" button but clicking the "View recommendation" button would take the user back there | #20 | No present action |  |  |  | Likely due to having multiple listings of the same game dependant on the platform. User likely visited two seperate listings for the same game. Potentially resolve later by adding a system to group similarly named games
Suggestion | Add a system so users can add games rather than relying soley on the gatherers | - | No action | Good idea but has some issues: 1. Malicious users could add bad data 2. Need things like official descriptions and screenshots and icons which a user might not be bothered to add or could add incorrect ones |  |  | I'm unsure how I feel about this. If we made sure our gatherer gathered the entire store - then this likely wouldn't be an issue. Just for the moment however gathering the entire store would take a long time, and a lot of storage space (for the screenshots). Adding opportunity for users to directly enter games seems like asking for trouble
Suggestion | Remove some duplicate categories such as "Local Multiplayer", "Multiplayer", etc | - | Same issue/suggestion as row 11 | Local multiplayer isn't the same as multiplayer (one uses local wifi for people in the same room, the other would be online)
Suggestion | Rename the website to something actually game related | - | No present action | Need ideas for this |  |  | Very good point, should consider this
Suggestion | A review section to offer additional feedback on a game rather than just stars | - | No present action | Good idea but would require changes to database, and it's too late for things like that |  |  | A decent idea, however currently outside of scope